## Sheet1
Week # | To Do | Owned by | Deadline | Status | Comments
Week 7 - Start up | Set up collab repository | Risheene | Aug 5,2019
Notes: Aug 5 - 12 | User needs | All | Aug 7, 2019 |  | high priority
| interview DO | All | Aug 8, 2019
| interview students | All | Aug 9,2019
| Interview guards | All | Aug 10,2019
| paper prototype | Jamie | Aug 12,2019 |  | high priority
Week 8 - Interview with Paper Proto | Interview DO with proto | All | 2013-08-01
Notes: 13-20 | Interview guards with proto | All | 2014-08-01
| Interview students with proto | All | 2015-08-01
| Revise User needs | All | 2017-08-01
| Point of view | All | 2018-08-01
| Plan changes | All | 2020-08-01
Week 9 - Digital Mockup | create ui for guard | risheene | 2021-08-01
Notes: 21-28 | create ui for students | risheene | 2022-08-01
| create ui for DO | jamie | 2023-08-01
| Design | jamie | 2024-08-01
| interview DO with digital mock up | all | 2026-08-01
| interview guard with digital mock up | all | 2027-08-01
| interview students with digital mock up | all | 2028-08-01
Week 10 - Adjustments for needfinding | do suggestions of the DO | jamie | 2029-08-01
| do suggestions of the Guards | risheene | 1930-08-01
Notes: 29- sept 5 | do suggestions of the students | risheene | 1931-08-01
| plan html/css | jamie | 2005-09-01
Week 11 - Plan website | login page | risheene | 2006-09-01
Notes: sept 6 - 13 | home page for students | jamie | 2007-09-01
| assign buttons needed | all | 2008-09-01
| home page for guards | jamie | 2009-09-01
| home page for DO | risheene | 2010-09-01
| Viewing lists for students | jamie | 2011-09-01
| viewing list for DO | jamie | 2012-09-01
| issue violations for guards and DO | jamie | 2013-09-01
Week 12 - Finalize paper and website | finalize UI for guards | jamie | 2014-09-01
Notes: sept 14 - 16 | finalize UI for students | jamie | 2014-09-01
| finalize UI for DO | jamie | 2014-09-01
| Revise Documentation | risheene | 2016-09-01